## Project Plan
| Ware Town Council |  |  | Actual |  |  | Budget
| Business Plan Projects | Actual | Forecast | Income | Expenditure | Surplus | Income | Expenditure | Surplus | [11 empty] | Expenditure | Expenditure | Expenditure | Expenditure | Expenditure
|  | 2013/14 | 2014/15 | 2018/19 | 2018/19 | / Deficit | 2019/20 | 2019/20 | / Deficit | [11 empty] | 2020/21 | 2021/22 | 2022/23 | 2023/24 | 2024/25
|  | £ | £ | £
[11 empty] | Sponsor | Project Mgr | Committee | Project Brief | Scoping meeting | Specification Approval | Quotes | Project Start | Project complete | Comments | [5 empty] | Budget
| Green issues leadership | [8 empty] | Comm | Martin Butcher | MB | C&E |  |  |  |  | 2020-04-01 |  |  | 5000 | 5000 | 5000 | 5000 | 5000 | Revenue
| Trees and Planters in suburbs | [8 empty] | Comm | Jonathan Kaye | MW/TP | C&E |  | 03.01.20 |  |  | 2020-04-01 |  |  | 20000 | 3000 | 3000 | 3000 | 3000 | Capital /Revenue
| Cycle Lanes | [8 empty] | Comm | Stephen Reed | SR | C&E |  |  |  |  | 2021-04-01 |  |  |  | 10000 |  |  |  | Capital
| Neighbourhood Plan | [8 empty] | Comm | Jan Stock | Jan Stock | WTC |  |  |  |  | 2021-04-01 |  |  |  | 9000 | 9000
| Outdoor activity days | [8 empty] | Event | Sean Shaw | RM | C&E |  |  |  |  | 2020-04-01 |  |  | 10000 | 10000 | 10000 | 10000 | 10000 | Revenue
| Ware Film Festival | [8 empty] | Event | Victoria Shaw | RM | C&E |  |  |  |  | 2020-04-01 |  |  | 5000 | 5000 | 5000 | 5000 | 5000 | Revenue
| Reducing loneliness | [8 empty] | Event | Mark Pope | RM | C&E |  |  |  |  | 2020-04-01 |  |  | 5000 | 5000 | 5000 | 5000 | 5000 | Revenue
| Equipment in Town Centre Chess etc | [8 empty] | Town | Alex Curtis | RM | C&E |  |  |  |  | 2020-04-01 |  |  | 20000 |  |  |  |  | Capital
| Empty shops more attractive | [8 empty] | Town | Rishi Fernando | RM | C&E |  |  |  |  | 2020-04-01 |  |  | 15000 | 15000 | 15000 | 15000 | 15000 | Capital /Revenue
| Christmas Lights | [8 empty] | Town | Terry Philpott | TP/RM | C&E |  |  |  |  | 2020-11-01 | 2020-12-01 |  | 25000 |  |  |  |  | Capital /Revenue
| CCTV upgrade | [8 empty] | Town | Terry Philpott | TP | C&E |  |  |  |  | 2022-04-01 | 2023-04-01 |  |  |  | 16000 | 16000 | 8000 | Capital /Revenue
| Digital Noticeboard | [8 empty] | Town | Terry Philpott | TP/RM | C&E |  |  |  |  | 2021-04-01 |  |  |  | 15000 | 2500 | 2500
| Play Area development | [8 empty] | Grounds | Terry Philpott | TP/SH | Priory |  |  |  |  | 2021-04-01 | 2022-04-01 |  |  | 120000 |  |  |  | Capital
| Skate Park | [8 empty] | Grounds | Sean Higgins | SH/TP | Priory |  |  |  |  | 2020-04-01 | 2022-04-01 |  | 120000 |  |  |  |  | Capital
| New mower | [8 empty] | Grounds | Matt Watkins | MW | Priory |  |  |  |  | 2021-04-01 | 2021-05-01 |  |  | 4500 |  |  |  | Capital
| Priory Road and path repairs | [8 empty] | Grounds | Matt Watkins | MW | Priory |  |  |  |  | 2024-04-01 | 2025-05-01 | [5 empty] | 40000 | Capital
| Priory Bridge | [8 empty] | Grounds | Matt Watkins | MW | Priory |  |  |  |  | 2020-04-01 | 2020-06-01 |  | 30000 |  |  |  |  | Capital
| Tree Survey | [8 empty] | Grounds | Matt Watkins | MW | WTC |  |  |  |  | 2021-04-01 | 2021-09-01 |  |  | 3000 |  |  |  | Revenue
| Cemetery Conservation Area | [8 empty] | Cemetery | Terry Philpott | MW/TP | C&E |  |  |  |  | 2020-04-01 | 2021-04-01 |  | 2500
| Memorial Testing | [8 empty] | Cemetery | Matt Watkins | MW | C&E |  |  |  |  | 2023-04-01 | 2023-09-01 |  |  |  |  | 4000 |  | Revenue
| Longer swim season Lido | [8 empty] | Lido | Dan Wateridge | DW | Priory | 2019-11-28 |  | 2019-12-11 |  | 2020-04-01 | 2020-11-01 | Trial | 28000 | 28000 | 28000 | 28000 | 28000 | Revenue
| Changing Room Flooring | [8 empty] | Lido | Dan Wateridge | DW/MW | Priory | 2019-12-31 |  |  |  | 2021-04-01 |  |  |  | 30000
| Outdoor showers | 8000 | [7 empty] | Lido | Dan Wateridge | DW/MW | Priory | 2019-12-31 |  |  |  | 2020-04-01 | 2020-06-01 |  | 5000
| Queuing system | 3000 | [7 empty] | Lido | Dan Wateridge | DW/MW | Priory | 2019-12-31 |  |  |  | 2020-04-01 | 2020-06-01 |  | 2000
| Shade for queue | 2000 | [7 empty] | Lido | Dan Wateridge | DW/MW | Priory | 2019-12-31 |  |  |  | 2020-04-01 | 2020-06-01 |  | 1000
| External TV | 2000 | [7 empty] | Lido | Dan Wateridge | DW/MW | Priory | 2019-12-31 |  |  |  | 2020-04-01 | 2020-06-01 |  | 2000
| Inflatable | 4275 | [7 empty] | Lido | Dan Wateridge | DW/MW | Priory | 2019-12-11 |  |  |  | 2020-06-01 | 2020-06-01 |  | 4275
| Office Kiosk | [8 empty] | Lido | Dan Wateridge | MW/DW | Priory |  |  | 2019-12-11 |  | 2020-04-01 | 2020-04-01
| Sunbeds | [8 empty] | Lido | Dan Wateridge | DW | Priory |  |  | 2019-12-11 |  | 2020-04-01 | 2020-06-01
| Pool Cover / Lifeguard Chair | [8 empty] | Lido | Dan Wateridge | DW | Priory |  |  | 2019-12-11 |  | 2020-04-01 | 2020-04-01
| Toilets upgrade Priory / FL | [8 empty] | Priory | Kerry Marvis | TP/MW/KM | Priory |  |  |  |  | 2020-08-01 |  |  | 20000 | 20000 | 10000 | 10000 |  | Capital
| Fletcher Lea upstairs* | [8 empty] | Priory | Phyllis Ballam | TP | Priory |  |  |  |  | 2020-04-01 | [6 empty] | 200000 | Capital
| FL Projector | [8 empty] | Priory | Sean Higgins | SH/KM | Priory |  |  |  |  | 2020-04-01 |  |  |  |  | 15000 |  |  | Capital
| FL Floor repairs | 4000 | [7 empty] | Priory | Matt Watkins | MW | Priory |  |  |  |  | 2020-04-01 |  |  | 4000
| FL Blinds | 6000 | [7 empty] | Priory | Sean Higgins | SH | Priory |  |  |  |  | 2020-04-01 |  |  | 6000
| FL External painting | 4000 | [7 empty] | Priory | Terry Philpott | MW | Priory |  |  |  |  | 2020-04-01 |  |  | 4000
| FL Drainage | 1600 | [7 empty] | Priory | Terry Philpott | MW | Priory |  |  |  |  | 2020-04-01 |  |  | 1600
| Quinquennial review urgent | [8 empty] | Priory | Terry Philpott | MW | Priory |  |  |  |  | 2020-04-01 |  |  | 15150 | 0 | 1500 | 0 | 20000
| Quinquennial review essential | [8 empty] | Priory | Terry Philpott | MW | Priory |  |  |  |  | 2020-04-01 |  |  | 8925 | 43700 | 0 | 0 | 0
| Quinquennial review desirable | [8 empty] | Priory | Terry Philpott | MW | Priory |  |  |  |  | 2020-04-01 |  |  | 2000 | 6750 | 138250 | 0 | 3600
| Quinquennial review Long term | [8 empty] | Priory | Terry Philpott | MW | Priory |  |  |  |  | 2020-04-01 |  |  | 0 | 1700 | 600 | 9450 | 27950
| Quinquennial review Annual Maintentance | [8 empty] | Priory | Terry Philpott | MW | Priory |  |  |  |  | 2020-04-01 |  |  | 14665 | 13665 | 13665 | 13665 | 14165
| PC Upgrade | [8 empty] | Admin | Sean Higgins | SH | F&P |  |  |  |  | 2020-04-01 |  |  | 5000
Lido | Opening 1st April 2021
Lido | Booking Website
Lido | Flooring
Priory | Vaccine Centre
Priory | New Catereres
Priory | Grounfd Floor toiopelts
Priory | First floor toilet
Priory | Reopening
Priory | Terms and Conditions
Communications | Digital Noticeboard
Communications | Customer Journey
Communications | Website
Communications | Marketing and Communications Plan
Communications | Annual Repaort
Grounds | Skate Pawrk
Grounds | Play Area project
Grounds | Tarmac quotes
IT | SAGE upgrade
IT | SAGE diary link
IT | SAGE invoice scanning
IT | Hardware Upgrades
IT | Priory WiFi
HR | Flexible working
Cemetery Officer Training
Fiaince | Year end accounts x 3
Green | ECO Audit
WTC | Election May 2021
NPF | Consultancy work
Locality Grant
Town Centre | CCTV review
Project funding
| New Homes Bonus | [19 empty] | 65000 | 65000 | 65000 | 60000
| CIL /106 | [19 empty] | 60000 | 60000
| Grants | [19 empty] | 6000 | 6000
| Locality Neighbourhood Plan | [21 empty] | 9000
| Total Projects | [19 empty] | 512115 | 479315 | 351515 | 186615 | 384715
Quinquennial review
| Urgent work | [19 empty] | 15150 | 0 | 1500 | 0 | 20000
| Essential work | [19 empty] | 8925 | 43700 | 0 | 0 | 0
| Desirable work | [19 empty] | 2000 | 6750 | 138250 | 0 | 3600
| Long term work | [19 empty] | 0 | 1700 | 600 | 9450 | 27950
| Annual Maintenance | [19 empty] | 14665 | 13665 | 13665 | 13665 | 14165
[6 empty] | 0 | [6 empty] | 0
| Contingency | [9 empty] | Target 33.3% precept c£300K | [9 empty] | 70000 | 70000 | 70000 | 70000 | 0
| New Homes Bonus | [9 empty] | Target £255438 | [9 empty] | 65000 | 65000 | 65000 | 60000 | 0
| Admin Contingency | [9 empty] | Target £20000 | [9 empty] | 0 | 0 | 10000 | 10000 | 0
| Priory Contingency* | [9 empty] | Target £200000 | [9 empty] | 0 | 0 | 100000 | 100000 | 0
| Total Reserves allocation | [19 empty] | 135000 | 135000 | 245000 | 240000 | 0