## Risk Management
Ware Town Council
Risk Management review
22.07.24
[15 empty] | Control | DoT
Risk Category | Subject | Nature of risk | Impact | Mitigation | Action Required | Lead Officer | How is risk managed | Likelihood | Impact | Risk after mitigation | Review date | Likelihood* | Impact* | Appetite*
Administration | Data and records | Total loss of electronic data. |  | All electronic records backed up daily onto cloud. SAGE backed up after each use. |  | TC | in-house |  |  | 6 | on-going | 1 | 3
Administration | Data and records | Total loss of hard copy records e.g. Fire. |  | All key records kept in a fireproof safe. Where possible keep electronic copy. For essential documents keep copy offsite. |  | TC | in-house |  |  | 12 | Annual | 2 | 4
Administration | Data protection Act | Non-compliance with legal requirements. |  | Employ qualified clerk. Advice received from NALC and SLCC re changes to legislation/regulation/best practice. Staff training. |  | RFO | in-house |  |  | 9 | Annual | 2 | 3
Administration | Fraud | Fraudster Hacking into system | Loss of access to the system | Check with IT provider that cyber security is sufficient |  | RFO | IT Provider |  |  | 9 | Annual | 2 | 3 |  | Passed Cyber Security Accreditation carried out by Alphafirst | ↓
Assets |  | Damage to Council owned property | High cost of repair, Disruption , damage or injury to third party | Assets insured, Value increased annual by RPI |  | RFO | in-house |  |  | 9 | n/a | 2 | 3 |  | Building valuation carried out for next year. | ↔
Assets |  | Loss / theft of asset equipment | Loss of asset, Disruption to services Cost of replacement | Alarm at WTC office. Contents and all assets insured. Asset register maintained. Inventory of equipment maintained and checked. All thefts reported to police. |  | OM | in-house |  |  | 9 | n/a | 2 | 3
Assets |  | Lack of maintenance of property and equipment owned or managed by Council. | Damage to property High cost of repair Damage or injury to third party. Claims against Council. | Regular routine maintenance Regular servicing of equipment Insurance cover Tree surveys carried out every 5 years. Cemetery memorial inspections carried out. Allotments maintained by Ware Allotment Garden Society. Common Wharf | .Next inspection due 2023.6 monthly inspections by WTC staff Inspect monthly and carry out any maintenance required. | Facilities Supervisor Town Clerk Allotment officer Facilities Supervisor | in-house |  |  | 5 | n/a | 4 | 1
Cemetery | Incorrect burial / records | Relatives stress. Reputational damage |  | Clerk / Deputy Clerk trained in cemetery management. Zero tolerance to incorrect paperwork from funeral directors. Revised T&C for cemetery |  | TC | in-house |  |  | 6 |  | 1 | 3
Cemetery | Headstones and memorials | Structural failure and damage presents risk to the public. |  | Maintenance contractor to monitor and topple test on behalf of the council and make safe where appropriate. 2023 survey completed. Owner to be responsible for repairs |  | FS | in house / 3rd party |  |  | 6 |  | 1 | 3 |  | Memorial tests to be carried out in 2023 and every 3 years.
Employer liability |  | Non-compliance with relevant laws:EmploymentHealth & SafetyEqualitiesDisability Discrimination Human Rights Data Protection | Employee action for negligence or grievance. Penalties from regulatory bodies. | WTC has a contract with EHDC for HR advice. Updates also received via HAPTC and SLCC.HR policies in place in staff handbook regularly reviewed. | Agreement with new provider agreed EHDC following tender process and meeting several possible providers. | TC | in-house |  |  | 6 | n/a | 2 | 2
Employer liability |  | Non-Compliance with HMRC requirements | Penalties from HMRC | Outsourced payroll provider deals with PAYE and NIC.VAT returns checked quarterly. |  | RFO | in-house |  |  | 4 | n/a | 1 | 2
Employer liability |  | Safety of staff and visitors | Damage or injury to third party. Injury to staff. Loss of working time. Claims against the Council. | Insurance in place. Annual health and safety audits carried. Health and Safety Action Planner produced for staff to work through. Action Planner and Accident Reports reviewed by Finance & Policy Committee. Staff handbook details staff responsibility for own health and safety. Visitors and contractors to sign in and out. |  | RFO | in-house |  |  | 9 | n/a | 2 | 3
Finance | Bank | Misuse of credit and debit cards | Loss of funds | Cards issued to Facilities Supervisor and Town Clerk and controlled by RFO. Monitored when account is reconciled. Financial regulations in place. |  | RFO | in-house |  |  | 4 | n/a | 1 | 2
Finance | Fraudulent Payments | Fraudulent invoice being paid | Loss of funds | All invoices to be double checked before payment. |  | RFO | in-house |  |  | 4 |  | 1 | 2
Finance | Bank collapse | Bank failure or loss of investments | Significant loss of funds. Inability to pay staff and suppliers. Inability to provide services. | Regular review. Keeping funds in low risk financial vehicles. Additional bank account to be opened. | Review of banking and investment arrangements. | RFO | in-house |  |  | 6 | n/a | 2 | 2 |  | Have opened accounts to invest reserves and continue to review regularly. | ↔
Finance | Borrowing | Non-compliance with borrowing restrictions | Inability of Council to repay loan. | Loan payments need to be paid over the next 10 years due to the PWLB loan need to ensure enough funds are available to make repayments. |  | TC | in-house |  |  | 6 | n/a | 1 | 3 |  | Budget Process ensures there will be enough funds to cover repayments until 2033. | ↓
Financial risks | Budgeting | Cash flow problems. |  | Monitor income timing. Increasing reserves in order to increase resillience. Continue to generate monthly monitoring reports. |  | RFO | in-house |  |  | 6 | Monthly | 2 | 2
Financial risks | Budgeting | Risk of significant overspend. |  | Monitoring procedures in place to control and report on all spending. Utilise General Reserves. Reduce other expenditure. Increase Precept. |  | RFO | in-house |  |  | 6 | Monthly | 2 | 2
Finance | Business Interruption | Consequential loss of income (business interruption) | Reduction in income. | Business interruption insurance in place. Apart from the precept, the only sources of income to WTC are cemetery. Allotments and events. |  | RFO | in-house |  |  | 9 | n/a | 2 | 3 |  | WTC Merged with WPT will review all income streams with the Clerk to ensure insurance is sufficient. | ↑
Financial risks | Capital Projects | Risk of financial overcommitment and cost overruns. |  | Council appoint working roups to monitor professional consultants. Check on programme and expenditure. Employ suitably qualified clerk. |  | TC | in-house |  |  | 6 | as required | 2 | 2
Finance | Cash Loss | Loss of cash through theft or dishonesty | Reduction in income. | Financial Regulations in place and reviewed regularly. Internal audit with twice yearly visits. Insurance in place. Receipts issued for cash. Cash held in locked tins and locked in safe in the evening. Cash banked regularly to minimise amount held. Cash takings reconciled when banked. Petty cash reconciled regularly using imprest system. |  | RFO | in-house |  |  | 4 | n/a | 1 | 2
Financial risks | Contracts | Risk of poor performance by contractors. |  | Council appoint working groups to monitor contractor's performance. In appropriate circumstances appoint a project Manager. Day to day services managed by Town Clerk. |  | TC | in-house |  |  | 6 | as required | 2 | 2
Finance | Controls | Inadequate financial controls and records | Risk of unbudgeted expenditure. Increased possibility of fraud. | Financial Regulations in place and reviewed regularly. Scheme of delegation in place and reviewed regularly. Internal audit with three yearly visits. Effectiveness of internal control and audit reviewed annually | Review at each Annual Meeting Review at each Annual Meeting | TC | in-house |  |  | 6 | n/a | 2 | 2
Finance | Fraud | Loss through fraud | Significant loss of funds. Inability to pay staff and suppliers. Inability to provide services. | Financial Regulations in place and reviewed regularly. Internal audit with twice yearly visits. Fidelity insurance in place. Bank payments to be authorised by two councillors. Bank reconciliations carried out monthly and checked by Town Clerk & 2 Members of the Council. Effectiveness of internal control and audit reviewed annually. Change in supplier bank details to be checked by staff with a phone call to verify correct data. |  | RFO | in-house |  |  | 6 | n/a | 2 | 2
Financial risks | Insurance | Is insurance cover adequate? |  | Professional advice sought and implemented. Market testing of insurance providers. |  | RFO | all 3 |  |  | 6 | Annual | 2 | 2
Financial risks | Investment Account major losses | Loss of funds |  | Regular review of financial investments. Spread risk complete also investigating other options. |  | RFO | in-house |  |  | 6 | Annual | 1 | 3
Financial risks | Pension | Pension commitments |  | Precept set for known requirements. Annual review of staff salaries. |  | RFO | in-house |  |  | 6 | Annual | 1 | 3
Finance | Precept | Inadequacy of precept | Unable to provide services and functions. Insufficient funds for contingencies and projects. | Chair and Vice Chair of Finance & Policy Committee discuss detailed draft budget with RFO. Draft budget considered in detail by Council. Quarterly budget reports to Finance & Policy Committee. | Develop strategic plan and 3 year financial plan | Council, Town Clerk and RFO | in-house |  |  | 4 | n/a | 1 | 2
Finance | Reserves | Inadequate reserves | Impact on ability to manage services and pay suppliers. Cashflow difficulties. Unable to finance unexpected or unbudgeted emergencies. | Proper internal control measures for managing expenditure within budget. Clear and appropriate budgeting. Strategic planning to focus resources | Develop strategic plan and 3 year financial plan | Council, Town Clerk and RFO | in-house |  |  | 6 | n/a | 2 | 2
Financial risks | VAT | Incorrect accounting for VAT liability. |  | Staff training. Internal audit. Transaction sums are relatively small. SAGE accounting. |  | RFO | in house |  |  | 6 | Annual | 2 | 2
Governance and reputational risk | Policies | Are policies and procedures fit for purpose | Public challenge, breach of statutory responsibility | Annual review of standing orders and Financial Regulations. Review of other policies as per schedule. |  | TC | in house |  |  | 6 | Annual | 2 | 2
Governance and reputational risk | Code of Conduct | Code of conduct, declarations of interests and dispensations | Reputational risk. Potential challenge to a resolution and the need to change a decision. Financial liability / impact. | Records of declarations of interest taken at each meeting. Code of conduct rules reviewed regularly. Peer knowledge of other councillors. | Councillor Training to be offered to councillors. | TC | in house |  |  | 9 | Annual | 2 | 3
Governance and reputational risk |  | Recording council resolutions | Public challenge. Unintended consequences from lack of clarity. | Draft minutes published within 2 weeks of meetings. Committees and Town Council approve minutes for accuracy. Staff attention to detail with the wording of minutes. |  | TC | in-house |  |  | 3 | Annual | 2 | 1
Governance and reputational risk |  | Over zealous risk management | Culture of no activity unless risk-free | Focus on being risk aware not risk averse. |  | TC | in-house |  |  | 3 | on-going | 2 | 1
Governance and reputational risk |  | Quality Council Award. | Not meeting the requirements for Quality Council status. | Clerk to monitor requirements are being met and make recommendations for improvement/change to TC. Council have acheived Gold level. |  | TC | in-house |  |  | 3 | Annual | 2 | 1
Governance and reputational risk |  | Ensuring activities are within legal powers | Risk of ultra vires spending and legal challenge. | WTC has Power of General Competence. Clerk to clarify position on any new proposal. Legal advice may also be obtained from HAPTC or NALC. | Confirmed eligibility for GPC at the first Annual Meeting after elections in May 2023 and all evidence sent to PKF external auditor. | Town Clerk | in-house |  |  | 6 | n/a | 1 | 3 |  | Evidence of GPC sent to PKF for external audit. | ↓
Governance and reputational risk |  | Proper and timely reporting via the minutes | Misunderstanding decisions taken. Actions not reflecting intentions of Council. | Minutes and pages sequentially numbered and held in minute book. Minutes approved by committees and Council. |  | TC | in-house |  |  | 4 | n/a | 3 | 1
Governance and reputational risk |  | Proper Document control | Loss of Key documents | Town Council owned land registered with land registry. Cemetery records scanned up to 2022 and put on Epitaph computer package. Minutes up to 2007 in bound books. Data protection measures in place to comply with GDPR. | Consider need to scan records from 2012.Consider need to scan minutes. | Town Clerk Town Clerk | in-house |  |  | 4 | n/a | 3 | 1
Governance and reputational risk |  | Councillors lack knowledge and skills | Council fails to achieve its purpose. Poor decision making. Decisions making by-passes Council. Lack of service to residents. Damage to reputation. | Induction pack for new councillors. Training by HAPT organised for whole Council after elections. Training for councillors available through HAPTC. Encourage good relationships between officers and councillors. | Consider how to improve attendance. | Council and Town Clerk Town Clerk and Leader of Council | in-house |  |  | 12 | n/a | 3 | 3 |  | Do Councillors need training ? | ↔
Governance and reputational risk |  | Council becomes dominated by one or two individuals or cliques form. | Conflicts of interest. Pursuit of personal agendas. Decisions made outside Council. | Clear Standing Orders in place regarding conduct of meetings. Code of Conduct in place. Training for councillors available through HAPTC. |  | TC | in-house |  |  | 9 | n/a | 2 | 3
Governance and reputational risk |  | Councillors benefitting from being on Council. | Conflicts of interest. Challenge to decisions. Loss of reputation. | Clear Standing Orders, Code of Conduct and Financial Regulations in place. Declarations on Interest is an agenda item at every meeting. |  | TC | in-house |  |  | 6 | n/a | 2 | 2
Governance and reputational risk |  | Failure to register and declare members’ interests and gifts and hospitality | Member could make inappropriate gains. Loss of reputation. | Clear Standing Orders and Code of Conduct in Place. Councillors required to register interests and gifts and keep updated. Training for staff and councillors on Code of Conduct. | Suggest councillors asked to provide annual updates. | Town Clerk | in-house |  |  | 6 | n/a | 2 | 2
Cemetery |  | Failure to carry out cemetery record checks. | Inaccurate allocation of exclusive rights. Inaccurate allocation of burial plots Distress to bereaved families. Loss of income. | Town Clerk signs off deeds or RFO in Clerks absence. Cemetery officer and Facilities Supervisor check records before burials. Two staff to check allocation of plot before digging takes place. |  | FS | in-house |  |  | 9 | n/a | 2 | 3
Legal and regulatory risks | promotion of disability equality. | Do buildings, land and facilities meet requirements of disability equality legislation? |  | Creation of Accessibility working party. Implement the policy on the promotion of disability equality in each area of activity. Advice received from NALC and SLCC re changes to legislation/regulation/best practice. |  | TC | in -house |  |  | 9 | Annual | 2 | 3
Legal and regulatory risks | Staff | Are employment practices fair and reasonable? |  | Advice received from NALC and SLCC re changes to legislation/regulation/ best practice. Employ professional clerk. Oversight by councillors through HR (reports to policy cttee). Feedback from annual staff performance review. |  | TC | in-house |  |  | 9 | Annual | 2 | 3
Legal and regulatory risks | Staff | Is the working environment safe for office staff? |  | Staff training in health and safety. Ensure appropriate specification for equipment and furniture purchases. |  | TC | in-house |  |  | 9 | Annual | 2 | 3
Legal and regulatory risks | Staff | Is the working environment safe for caretaking staff? |  | Staff training in health and safety. Ensure appropriate specification for equipment purchases. "Door safe" staff used at events. |  | TC | in-house |  |  | 9 | Annual | 2 | 3
Legal and regulatory risks | Staff | Loss of key staff. | Would cause issues if we lose key personnel for long periods of time. | Role sharing during sickness and holiday avoids dependency on one employee for any activity. Annual performance review. Fair employment conditions. Flexible working. Business Continuity plan. Efficient recruitment process. Succession planning. |  | TC | in -house |  |  | 9 | on-going | 2 | 3 |  | Further training on cover in all areas. Flexible working to continue. Business Continuity Plans in place for all staff. | ↔
Legal and regulatory risks | Staff | Risk of employment dispute, claim for injury, stress, harassment, unfair/constructive dismissal. |  | Use appropriate terms and conditions of employment. Performance review process. Awareness by councillors of potential problems among staff. Support available from SLCC and NALC. |  | TC | in-house |  |  | 12 | on-going | 2 | 4 |  | Monthly Team Meetings, Quarterly reviews for Senior Management and Annual appraisals for all staff. | ↔
Legal and regulatory risks |  | Requirements of equal opportunities and diversity legislation. |  | Employment of qualified clerk. Advice received from NALC and SLCC re changes to legislation/ regulation/best practice. |  | Council | in-house |  |  | 8 | Annual | 3 | 2
Liability |  | Risk to third party, property or individuals | Damage or injury to third party. Claims against the Council. | Insurance in place.WTC has a contract in place with EHDC for Health & Safety Advice and to act as Competent Person. Annual health and safety audits carried. Health and Safety Action Planner produced for staff to work through. Action Planner and Accident Reports reviewed by Council. |  | RFO | in-house |  |  | 12 | n/a | 2 | 4 |  | Are EHDC still involved ?
Liability |  | Legal liability as consequence of asset ownership or management (especially burial ground, Common Wharf) | Damage or injury to third party. Claims against the Council. | Regular routine maintenance Insurance cover Tree surveys carried out every 5 years. Cemetery memorial inspections carried out every 3 years. Allotments maintained by Ware Allotment Garden Society. Common Wharf | Next surveys due 2027.Next inspection due 2026. 6 monthly inspections by WTC staff Inspect monthly and carry out any maintenance required. | Facilities Supervisor Town Clerk Allotment officer Facilities Supervisor | in-house |  |  | 12 | n/a | 2 | 4
Stalls / External events | Stalls | Are stall-holders insured? i.e. Avoiding risk of potential claim against Town Council |  | Operator to ensure all stall holders have adequate insurance. Refuse to allow non-insured stall-holder to attend market. |  | EM | 3rd party |  |  | 12 | Annual | 3 | 3
Stalls / External events | Stalls | Is location safe? |  | Risk assessment carried out. |  | EM | 3rd party |  |  | 9 | Annual | 2 | 3
Operational risks | CCTV Cameras | Failure to record or identify an incident. |  | New CCTV now installed April 2023 |  | TC | in-house |  |  | 6 | Annual | 2 | 2
Operational risks | Christmas Lights | Risk to the public of lights falling or catching fire. |  | Installation by experienced contractors, with completed risk assessment, and regular monitoring, especially by members of the public. Annual PAT testing of lights. |  | FS | in-house |  |  | 9 | Annual | 2 | 3
Operational risks | Safety of trees. | Structural failure and damage presents risk to the public. |  | Annual inspection by tree warden and report to TC. Expert advice sought if required. 3-yearly full risk assessment of trees. |  | FS | in-house |  |  | 12 | Quarterly | 2 | 4
Operational risks | lamp posts / flagpoles | Fatigue and Failure. |  | Annual inspection. Feedback from residents. |  | FS | in-house |  |  | 6 | Annual | 2 | 2
Operational risks | Risk of flooding | Damage to property, potential injury |  | Business Continuity plan.Emergency Plan . Regular maintenance schedule. Adequate insurance. |  | TC/RFO | 3rd party |  |  | 12 | Annual | 2 | 4
Play Areas | Priory Grounds | Risk of trespass. |  | Regular usage of the area is a deterrent. Entrance gate can be locked. |  | FS | in house |  |  | 8 | on-going | 3 | 2
Play Areas | Priory Grounds | Structural failure and damage presents risk to the public. |  | Regular inspections by Cllrs, quarterly inspection , Annual by Maintenance Manager. |  | FS/COUNCIL | in house / 3rd party |  |  | 12 | on-going | 2 | 4
Play Areas | Priory Grounds | Expensive repairs required to keep the structures safe. |  | Regular inspections. Earmarked reserves to cover unbudgeted costs. |  | FS | in house |  |  | 9 | on-going | 2 | 3
Priory Building | Council Offices | Destruction of Priory leading to loss of income. |  | Fire detection systems installed and maintained. Policy forbidding hirers from using flammable material. Flammable materials stored externally. |  | FS | all 3 |  |  | 12 | Annual | 2 | 4
Priory Building | Council Offices | Risk of major fire |  | Smoke alarms tested weekly; fire extinguishers tested annually. Annual test of systems b y approved contractor. Policy forbidding hirers from using flammable material. |  | FS | all 3 |  |  | 12 | weekly/Annual | 2 | 4
Priory Building | Council Offices | Loss of council office and meeting rooms. |  | Hire replacement facilities within Ware. Measures taken to protect building. |  | FS | all 3 |  |  | 12 | n/a | 2 | 4
Priory Building | Council Offices | Is the building structurally sound? |  | Daily use ensures issues are identified. Concerns would be addressed by using specialist firms. |  | COUNCIL/FS | in house |  |  | 9 | Annual | 2 | 3
Priory Building | Council Offices | Is the building secure from intruders? |  | All entry points lockable. Valuable items locked away. |  | FS | in-house |  |  | 9 | Daily | 2 | 3
Priory Building | Council Offices | Are electrics and electrical equipment safe? |  | Annual PAT testing by suitably qualified contractor. Equipment purchased from reputable suppliers. |  | FS/OM | 3rd party |  |  | 6 | Annual | 2 | 2
Priory Building | Council Offices | Gas supply safe? |  | Annual testing by suitably qualified contractor. |  | FS | 3rd party |  |  | 9 | Annual | 2 | 3
Priory Building | Council Offices | Risks to hirers. |  | Employing good practice in building management. Information provided to hirers on health and safety. |  | FS/OM | in-house |  |  | 9 |  | 2 | 3
Priory Building | Council Offices | Destructive event e.g. Flooding |  | Business Continuity plan. Regular maintenance schedule. Adequate insurance. |  | TC/RFO | in-house |  |  | 16 | n/a | 3 | 4
Suppliers | Purchasing of goods and services | Not suitable for use and/or overpriced. |  | Council procedures in place requiring competitive quotations and expert advice sought where necessary. |  | TC/RFO | in-house |  |  | 8 | on-going | 3 | 2
Suppliers | Third party suppliers | Reputational risk of using suppliers who get adverse publicity. |  | Ensuring good quality specification for goods and services. References may be obtained before appointing suppliers. |  | TC/RFO | in-house |  |  | 8 | Annual | 3 | 2
Suppliers | Contractors supplying goods and services | poor performance. |  | Ensuring good quality specification. Regular monitoring of performance, either by TC or appointed consultants. |  | TC/RFO | in-house |  |  | 8 | on-going | 3 | 2
Trusts | Ware Priory Charity (WTC as sole trustee) | Financial failure |  | Monthly review of finances by RFO / Clerk. |  | TC/RFO | in house / 3rd party |  |  | 12 | on-going | 2 | 4
Trusts | Ware Priory Charity (WTC as sole trustee) | Major risk of trespass e.g. Travellers, fire or other risk to health. |  | Grounds no longer locked up each day due to Electric charging points. Police also attend the grounds regularly. |  |  | in house / 3rd party |  |  | 12 | Annual | 3 | 3 |  |  | ↑
Avg
[10 empty] | 7.969 |  | 2.0132 | 2.6447 | 5.3243
[9 empty] | Red | 3 | 3.896%
[9 empty] | Amber | 47 | 61.04%
[9 empty] | Green | 27 | 35.06%
77

## Scoring matrix
| Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7
WARE TOWN COUNCIL
RISK ASSESSMENT SCORING MATRIX
Impact | extreme | 5 | 10 | 15 | 20 | 25 | 30
| major | 4 | 8 | 12 | 16 | 20 | 24
| moderate | 3 | 6 | 9 | 12 | 15 | 18
| minor | 2 | 4 | 6 | 8 | 10 | 12
| insignificant | 1 | 2 | 3 | 4 | 5 | 6
|  |  | 1 | 2 | 3 | 4 | 5
|  |  | remote | unlikely | possible | probable | highly probable
Likelihood
The risk is assessed AFTER mitigation measures have been taken to reduce the identified risks.
calculation: xy+y
X= Likelihood
Y= Impact
Likelihood
| remote | 5 4 3 2 1: million to one chance
| unlikely | 5 4 3 2 1: 1 in 100000 chance
| possible | 5 4 3 2 1: 1 in 10000 chance
| probable | 5 4 3 2 1: 1 in 1000 chance
| highly probable | 5 4 3 2 1: 1 in 100 chance
Impact
| Insignificant | 5 4 3 2 1: Negligible
| Minor | 5 4 3 2 1: Low financial <£2K / personal injury (first aid)
| Moderate | 5 4 3 2 1: Medium financial<£10K / 3 days absence
| Major | 5 4 3 2 1: Financial>£10K / more than 3 days absence
| extreme | 5 4 3 2 1: significant cost>£50K / Life changing

## Appetite
Ware Town Council: Risk Appetite
The risk appetite description sets out how we balance risk and opportunity in pursuit of achieving our objectives. It forms a key element of our governance and reporting framework and is reviewed by the Council annually.
Appetite | Description
Averse | Avoidance of risk and uncertainty in achievement of key deliverable or initiatives is paramount. Activities undertaken will only be those considered to carry virtually no inherent risk.
Minimalist | Predilection to undertake activities considered to be very safe in the achievement of key deliverables or initiatives. Activities will only be undertaken where they have a low degree of inherent risk. The associated potential for reward/pursuit of opportunity is not a key driver in selecting activities.
Cautious | Willingness to accept / tolerate a degree of risk in selecting which activities to undertake to achieve key deliverables or initiatives, where we have identified scope to achieve significant reward and or realise an opportunity.
Open | Undertakes activities by seeking to achieve a balance between a high likelihood of successful delivery and a high degree of reward and value for money. Activities themselves may potentially carry , or contribute to, a high degree of residual risk.
Hungry | Eager to be innovative and choose activities that focus on maximising opportunities (additional benefits and goals) and offering potentially very high reward, even if those activities carry a high degree of residual risk.